## Sheet1
n | Review Date | Deliverable Reviewed | Required Findings | Actual Findings | Resolution | Sign off
QL‑01 | 01-Apr | Project Overview | Clear scope, objectives, and actors defined (Admin/Driver/Passenger) | Scope, roles and CRUD business rules clearly documented | No changes required | Scrum Master
QL‑02 | 02-Apr | Product Backlog | All 20 story cards mapped to business benefits | Story list aligned with role-based CRUD goals | Approved | Scrum Master
QL‑03 | 02-Apr | User Story Case Study (US01, US20 - Login/Logout) | Role-based login redirects to correct home page; session cleared on logout | Logout did not clear browser cache, back button still worked | Cache-clearing logic added on logout | Scrum Master
QL‑04 | 03-Apr | Sprint Backlog | Task-level breakdown with effort estimates for all 20 story cards | Initial effort mismatch identified for Driver/Ride modules | Backlog updated with accurate estimates | Scrum Master
QL‑05 | 03-Apr | Driver Creation (US02) | Driver ID must be a unique 5-digit random number; default password; status inactive | Duplicate Driver ID generated on concurrent creation | Uniqueness check added before insert | Scrum Master
QL‑06 | 04-Apr | Driver Registration (US08) | Driver ID 7-digit random number; License Number 7-digit prefixed with LI | License Number format not validated on save | Regex validation added for LI prefix format | Scrum Master
QL‑07 | 04-Apr | View & Terminate Drivers (US03, US04) | Terminate allowed only when Rides>10, Earnings>5000, Avg_Rating<3.0 | Termination allowed even when conditions not met | Business rule validation corrected before status update | Scrum Master
QL‑08 | 05-Apr | Ride Creation & Approval (US09, US06) | New ride saved as inactive; admin approval flips status to active | Ride became active without admin approval | Approval workflow enforced before status change | Scrum Master
QL‑09 | 05-Apr | Edit/Cancel Ride (US11, US12) | Ride details modified via race_id; admin approval required to re-activate | Ride edits skipped approval step and went live directly | Approval gate re-added for edit and cancel flows | Scrum Master
QL‑10 | 06-Apr | Passenger Registration (US14) | Passenger ID 7-digit random number; unique email and mobile | Duplicate mobile number accepted for two passengers | Uniqueness validation added on email and mobile | Scrum Master
QL‑11 | 06-Apr | Browse & Book Ride (US15, US16) | Only active rides shown in grid; booking reflects in Bookings History | Inactive rides appeared in passenger browse grid | Query filter corrected to show active rides only | Scrum Master
QL‑12 | 07-Apr | Rating Driver (US17) | Rating (1.0-5.0) allowed only when ride_status is Completed | Rating option was enabled for In Progress rides | Rating control disabled until ride_status = Completed | Scrum Master
QL‑13 | 07-Apr | Deactivate Account (US19) | Deactivated passenger status set inactive and blocked from login | Deactivated passenger could still log in once | Login check updated to verify registration_status | Scrum Master
QL‑14 | 08-Apr | Admin Activity Audit Trail (US07) | All CRUD actions logged in audit_logs; exportable as .csv | Delete actions on Ratings were not logged | Audit logging extended to cover Rating deletes | Scrum Master
QL‑15 | 08-Apr | Non-Functional Requirements | Must align with actual implementation (session handling, validations) | NFR document referenced outdated session timeout value | NFR corrected to match implemented session policy | Scrum Master
QL‑16 | 09-Apr | UI & Responsiveness | Screens must work across desktop and mobile devices | Ride grid layout broke on mobile view | Responsive grid CSS fixed | Scrum Master
QL‑17 | 09-Apr | Codebase Document | Clear architecture and role-based module structure explained | Documentation complete and accurate | Approved | Scrum Master
QL‑18 | 10-Apr | Final Demo Readiness | End-to-end flow (login to rating) works without errors | All major flows validated across Admin, Driver and Passenger roles | Approved for Final Review