## Sprint Backlog
Epic | Story Card | Source US | Task | Task Details | Priority | Story Points | Sprint | Status | Dependencies
Authentication | Role-Based Login | US01 | Login | Authenticate admin/driver/passenger and redirect to role-based home page | High | 5 | 1 | To Do
Authentication | Logout | US20 | Logout | Confirm logout, expire session, and clear browser cache | High | 2 | 1 | To Do | US01
Admin - Driver Management | Driver Management (Admin) | US02 | Create Driver | Create driver account with default password, 5-digit ID, inactive status | High | 5 | 1 | To Do | US01
Admin - Driver Management | Driver Management (Admin) | US03 | Read Driver | View driver records filtered by registration_status, sortable by rating/date | Medium | 3 | 1 | To Do | US02
Admin - Driver Management | Driver Management (Admin) | US04 | Update Driver | Terminate low-performing drivers by updating status active to inactive | Medium | 3 | 2 | To Do | US03
Admin - Passenger Oversight | Passenger Oversight (Admin) | US05 | Read Passenger | View passenger records sorted by no. of rides, filterable by status | Medium | 3 | 1 | To Do | US14
Admin - Ride Approval | Ride Approval (Admin) | US06 | Approve Ride | Approve driver requests to add, modify, or delete rides | High | 5 | 2 | To Do | US09
Admin - Audit Trail | Audit Trail (Admin) | US07 | Maintain Audit Logs | Log all CRUD actions for Driver, Passenger, Ride, Booking, and Rating; export as CSV | Medium | 5 | 4 | To Do
Driver - Profile Management | Driver Profile Management | US08 | Create Driver Profile | Self-register driver account with 7-digit ID and LI-prefixed license number | High | 5 | 1 | To Do
Driver - Profile Management | Driver Profile Management | US13 | Update Driver Profile | Edit driver profile fields except Driver ID and License Number | Medium | 3 | 2 | To Do | US08
Driver - Ride Management | Ride Management (Driver) | US09 | Create Ride | Add new ride with inactive status, pending admin approval | High | 5 | 2 | To Do | US08
Driver - Ride Management | Ride Management (Driver) | US10 | Read Ride | View rides by registration_status, sortable by fare and distance | Medium | 3 | 2 | To Do | US09
Driver - Ride Management | Ride Management (Driver) | US11 | Update Ride | Edit ride details by race_id; status reverts to inactive pending re-approval | Medium | 5 | 2 | To Do | US09
Driver - Ride Management | Ride Management (Driver) | US12 | Delete Ride | Cancel ride by race_id, pending admin approval to deactivate | Medium | 3 | 2 | To Do | US09
Passenger - Profile Management | Passenger Profile Management | US14 | Create Passenger Profile | Self-register passenger account with 7-digit ID and input validations | High | 5 | 1 | To Do
Passenger - Profile Management | Passenger Profile Management | US18 | Update Passenger Profile | Edit passenger profile fields except Passenger ID | Medium | 3 | 2 | To Do | US14
Passenger - Profile Management | Passenger Profile Management | US19 | Delete Passenger Profile | Deactivate account by updating status active to inactive; blocks login | Medium | 2 | 3 | To Do | US14
Passenger - Ride Booking | Ride Booking (Passenger) | US15 | Browse Rides | View active rides in grid format with driver and ride details | High | 3 | 2 | To Do | US10
Passenger - Ride Booking | Ride Booking (Passenger) | US16 | Book Ride | Book an active ride; record in booking history sortable by date | High | 5 | 3 | To Do | US15
Passenger - Rating | Driver Rating (Passenger) | US17 | Rate Driver | Rate driver 1.0 to 5.0 once ride status is Completed | Medium | 3 | 3 | To Do | US16
Sprint | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4
Initial Estimation Trend (Story Points) | 28 | 33 | 10 | 5
Actual Estimation Trend (Story Points) | 0 | 0 | 0 | 0