## Sheet1
n | Review Date | Deliverable Reviewed | Required Findings | Actual Findings | Resolution | Sign off
QL‑01 | 31-Mar | Project Overview | Clear scope, objectives, and actors defined | Scope and actors (Admin, Driver, Passenger) clearly documented | No changes required | Scrum Master
QL‑02 | 01-Apr | Product Backlog | All story cards mapped to business benefits | Story cards linked with proper priority and benefit | Approved | Scrum Master
QL‑03 | 02-Apr | User Story Case Study | Complete functional coverage with acceptance criteria | Minor wording inconsistency found in Driver ID length | User story updated ‑ Driver ID confirmed as 7-digit number | Scrum Master
QL‑04 | 03-Apr | Sprint Backlog | Task-level breakdown with effort estimates | Initial effort mismatch identified in ride approval tasks | Backlog updated with accurate estimates (132 hrs) | Scrum Master
QL‑05 | 04-Apr | Role-Based Access Implementation | Access restricted per role (Admin/Driver/Passenger) | Passenger was able to open driver's edit ride screen | Role checks corrected in code | Scrum Master
QL‑06 | 05-Apr | Driver Registration | New driver account must be inactive with default password | Registration_status was set to active by default | Fixed to set registration_status as inactive on creation | Scrum Master
QL‑07 | 06-Apr | Ride Creation & Approval Flow | New ride must stay inactive until admin approval | Ride was going live without waiting for admin approval | Approval step added before ride status changes to active | Scrum Master
QL‑08 | 07-Apr | Driver Termination Logic | Terminate only if Rides>10, Earnings>5000 and Rating<3.0 | Terminate button was enabled even when conditions were not met | Condition check added before enabling Terminate button | Scrum Master
QL‑09 | 08-Apr | Ride Booking Flow | Passenger can browse and book only active rides | Inactive rides were also showing up in Browse Rides page | Filter added to display only active rides | Scrum Master
QL‑10 | 08-Apr | Rating & Feedback | Rating allowed only when ride status is Completed | Rating option was visible even for In Progress rides | Rating enabled only after ride status is Completed | Scrum Master
QL‑11 | 09-Apr | Admin Audit Trail | Admin can export audit_logs table as .csv file | Export button was missing on audit log screen | Export to CSV option added for audit_logs | Scrum Master
QL‑12 | 09-Apr | UI & Responsiveness | Screens must work properly across devices | Ride list grid was breaking on mobile screen | UI responsiveness fixed for grid view | Scrum Master
QL‑13 | 10-Apr | Codebase Document | Clear architecture and structure explained | Documentation complete and accurate | Approved | Scrum Master
QL‑14 | 10-Apr | Final Demo Readiness | End-to-end flow works without errors | All major flows (login, ride booking, approval, rating) validated | Approved for Final Review | Scrum Master