## Sprint Backlog
Story | Sprint Backlog Item | Task | Volunteer | Task Details | Initial Effort | Day 1 Rem | Day 2 Rem | Day 3 Rem | Status
US01 | Authentication | Role-based Login | TBD | Login with role-based redirect to Admin/Driver/Passenger home page; only active accounts allowed | 5 | 5 |  |  | To Do
US02 | Driver Management | Create Driver | TBD | Admin creates driver account with default password, inactive status, 5-digit Driver ID, unique email/mobile | 5 | 5 |  |  | To Do
US03 | Driver Management | View Registered Drivers | TBD | Admin views drivers by registration_status; sort by Avg_Rating and registration_date | 4 | 4 |  |  | To Do
US04 | Driver Management | Terminate Driver | TBD | Admin terminates low-performing drivers (Rides>10, Earnings>5000, Rating<3.0), status active->inactive | 4 | 4 |  |  | To Do
US05 | Passenger Management | View Registered Passengers | TBD | Admin views passengers sorted descending by no. of rides; filter by registration_status | 4 | 4 |  |  | To Do
US06 | Ride Management | Approve Ride | TBD | Admin approves driver add/modify/delete ride requests; changes reflected in database | 5 | 5 |  |  | To Do
US07 | Audit | Admin Activity Audit Trail | TBD | Log CRUD operations (Driver, Passenger, Ride, Rating) to audit_logs table; export as .csv | 6 | 6 |  |  | To Do
US08 | Driver Registration | Register Driver Account | TBD | Driver self-registers; 7-digit Driver ID, License Number 7-digit prefixed 'LI' | 5 | 5 |  |  | To Do
US09 | Ride Management | Create Ride | TBD | Driver creates ride with inactive status; becomes active after admin approval | 6 | 6 |  |  | To Do
US10 | Ride Management | View All Rides | TBD | Driver views rides by registration_status; sort descending by fare and distance | 4 | 4 |  |  | To Do
US11 | Ride Management | Edit Ride Details | TBD | Driver edits ride by ride_id, status active->inactive; active again after admin approval | 5 | 5 |  |  | To Do
US12 | Ride Management | Cancel Ride | TBD | Driver cancels ride by ride_id; status active->inactive after admin approval | 4 | 4 |  |  | To Do
US13 | Driver Profile | Update Driver Profile | TBD | Driver updates profile (except Driver ID and License Number) with input validations | 4 | 4 |  |  | To Do
US14 | Passenger Registration | Register Passenger Account | TBD | Passenger self-registers; 7-digit Passenger ID, unique email/mobile, input validations | 5 | 5 |  |  | To Do
US15 | Ride Booking | Browse Rides | TBD | Passenger views all active rides in grid format with driver and ride details | 4 | 4 |  |  | To Do
US16 | Ride Booking | Book Ride | TBD | Passenger books an active ride; booking shown in Booking History, sortable by booking date | 6 | 6 |  |  | To Do
US17 | Rating | Rate Driver | TBD | Passenger rates driver (1.0-5.0) once ride_status is Completed | 4 | 4 |  |  | To Do
US18 | Passenger Profile | Update Passenger Profile | TBD | Passenger updates profile (except Passenger ID) with input validations | 4 | 4 |  |  | To Do
US19 | Passenger Profile | Deactivate Account | TBD | Passenger deactivates account, status active->inactive; can no longer login | 3 | 3 |  |  | To Do
US20 | Authentication | Logout | TBD | Logout with confirmation pop-up; session expired and browser cache cleared | 3 | 3 |  |  | To Do

## burntdown_chart
| Day 0 | Day 1 | Day 2 | Day 3
Initial estimation trend | 90 | 60 | 30 | 0
Actual estimation trend | 90 | 90 | 0 | 0